## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/7 - 9/20 | Github setup, Project idea finalized, Roles assigned, and SPPP DOC finalized | No serious tech issues reported | team 4 team name and logo still in process of being developed | still in development phase
1 | 9/21 - 10/18 | Frontend code skeleton created and added to GitHub. SDD document complete, SPPP updated, User Stories have started to be moved to backlog | There was one instance where the README.md file was mssing a step to get our app to run, but it was quickly rectified | bit of a learning curve working off of pivotal tracker | Get all team members to take ownership of User Stories in the backlog and implement the design on our code and build out the backend
2 | 10/19 - 11/8 | Our team was able to integrate the figma design into the front end using material ui, tsx and css. Most members were successful in contributing code to GitHub and we were able to follow our own QA guidelines. We were able to build out the backend and include tests | No significant technical issues, but some members struggled with time management and coding using material ui | Some members could have asked more experienced members for help on reaching their goals, while others were able to meet their goals and ask for help. | Time management could be improved. As TL I plan to ask members to take more ownership of their project goals and strongly encourage the team to be accountable and ask for help when they need it. |  |  | 24 | 16 | 8 |  |  | 6.5
3 | 11/9 - 12/6 | Team 4 has joined the frontend and the back-end. Added essential features like search, Dr. login, issuing prescritpion (from a dr panel, adding items to cart, prescription refill, and checkout | Deployment was an issue. We planned to deploy on heroku and have aws be a backup, but we ran into issues | There were a few non-technical issues that we tried to resolve via discord like keeping on track with our goals | Team members took initiative and organically implemented Risk Management plans on their own with coming up with solutions that they could remedy on their own. | 5 |  |  |  |  | 181.5 |  | 8

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Ryan Burns | I helped draft and proof read this document. I volunteered to make sure this document matched iteration 3 | Created at least 2 user stories about search and categorization | I supported my teams decision to go with a MVVM model | I delegated responsibilites for Testing documentation to more experienced developers while I focused on learning TDD | Presented in Iteration 1 with Cristol & will present with my team on 12/7 | I contributed to the front end first by attempting to create a working serach bar that was later perfected by Zahit who created an amazing navBar. I successfully implemented the category section of the landing page. I attempted many times to implement the shopping icon and the cart functionality but I ran into issues. I quickly turned to my team for support for sake of time. I worked mostly on the front end and created multiple feature branches that were merged into the development branch where I had my team review in pull requests. | My main focus was to learn the basics of TDD since this is a new concept to me. | I supported my teams decision to deploy our site on either AWS or Heroku | I organized all meetings and managed who took minutes. | As Team Leader, I planned and coordinated all team meetings consistantly this semester never missing one meeting. I prioritized my time to cultivate cohesion and communication between team members. I encouraged feedback from more experienced developers to help direct the teams' focus so to avoid double work and keep on track towards building a presentable product. I made sure to make myself available to members and provided support when they requested it.
Chenfei Yu(Christol) | Worte configuration management plans | Wrote several user stories related to user center, added new tags and optimize the classification of user stories | Wrote front-end code design and design patterns, includingpattern diagram. |  | Presented in Iteration 1, prepared the slides | Implemented home page, shopping page, and create prescription page. Functionalities included: Search for non-prescribed medcines, filter items by category, dynamically search for prescribed medicines in doctor's page and add them to prescription, retreive prescription. |  | Configured ESLint and Prettier for code format check. Configured git hooks for commit messages formatting and pre-commit code check and fixes. Designed and configured frontend code structure. | Designed the branching and issue mechanism we use. Attended meetings and wotre meeting minutes. | I initialized the frontend project with Zahit. We didn't use any code base from anyone else.
Youqing Shao(Tsing) | Worte security management, git flow and other infrastructures | Wrote down user stories related to user center, patient signup | Wrote down security management docs and some parts of configuration | Generated testing for the User Model and the API | Presented in Iteration 2 and literation 3, prepared the two literation slides | * Sign in / up, change password (full stack) * Designed jwt, developed permission authentication * Backend template (node + express) configuration with Zahit * Project security docs and actions * Node.js middleware and error interceptpor * whole project API request interaction * Email system for signup and order * Deployment herotu & aws clound * new technology exploring | Generated User management Testing. | * search for deployment using EC2 and Herotu * two end API Interaction * jwt perssion management * back-end template with Zahit * error interceptor and middleware api * tools of sending email | * help other member to fix bugd * Attended meetings and wotre a couple of meeting minutes actively * initiative to push project process with Christol and Zahit | In the project, I have ownership and push project progress, advance technology selection and avoid potential project risks, as an experienced developer, responsible for full-stack development, take the initiative to explore new and difficult technologies, actively cooperate with the team and take many detours less
Ignacio Joaquin Moral | Wrote Functional and Non Functional Requirements and User Stories, updated Management Plan Timeline for Iteration 3. | Generated User Stories and Acceptance Tests, managed user stories acceptance/decline | Included Class Diagrams and Business Logic Diagrams | Generated testing for the Prescription Model and the API | Presented in Iteration 2 with Tsing | Contributed to Prescription Creation Model, Controller, Routes, and Testing. | Generated Prescription Creation Testing. |  | I wrote some minutes in the Minute Tracker for our weekly meetings | Generated main order for Presentations, worked with Pivotal Tracker
Zahit Odabas | Contributed to Overview and Proposed High Level Requirements sections. Wrote QA Plan section. | Created 2 user stories with possible blockers, subtasks and acceptance tests in PivotalTracker. | Added Software Architecture Overview, Backend Project Structure and Database Schema. Contributed to Security Design | Created and updated the STD document. | - Presented in Iteration 0 and Iteration 3. - Prepared the final project video - Reviewed Iteration 1 presentation with Ryan and Christol. - Reviewed Iteration 2 presentation with Tsing and Ignacio. | - General design of the system, possible use cases and features - Mongo Cloud Database and backend integration - Backend => Backend template (node + express) configuration with Tsing, Backend project structure, Item(medicine) model, controller, API and tests - Frontend => Frontend template (vite) configuration with Christol - UI => Navbar, Searchbar, Banner, Prescription Drawer, Shopping page Category Filter, Shopping Cart - Checkout Page with all UI, functionalities and backend integration. Frontend test cases - Code reviewing, bug-fixing, refactoring | - Creating the testing environment for backend and frontend - Item (medicine) model and API tests for backend - 2 UI component tests for frontend - Genreating coverage reports | - Worked with Christol configuring ESLint + Prettier and Husky - Worked with Tsing configuring Express.js routing and adding interceptors - Merging seperate backend and frontend branches into 1 branch. | - Attended meetings and made suggestions about project. Contributed to meeting minutes document. - Helped team members in a timely manner - Arranged additional 1-1 meetings with peers when needed - Ensured tracking the general process of the project. Suggested work distribution and weekly reporting. | I've learned so much from and enjoyed this project. I've also learned from team members, particularly from Christol and Tsing. Me and Christol have worked intensively for the last weeks to make our project ready.
Nivan Hanjura | Contributed to the frontend logic and added the buisness logic for the cart management and product addition. Added the buisness logic for doctor prescription and added frontend test cases. | Wrote user stories about the context management and the story for not allowing to user to add items to cart without prescription for prescribed medicines. | Wrote the whole front end code using React and JavaScript and also using Jest. Added the functionality for add ing doctor prescription. | Added the frontend test cases. | Presented the team design,logic and in iteration 0 and discussed the plans. Presented in fianl iteration. | - Implemented the front code and logic for cart addition and manipulation for adding items into cart and also the logic for manipulating state wide. -Implemented the doctor's UI for adding,removing prescription and updating using Figma,Typescript and javascript. -Added front end test cases for login,signup and forgot password. | -Minor test cases for frontend to increase the testing coverage for frontend. | -Helped ryan configure some of the pages in front end as he had difficulty understanding javascript. -Wrote a context api for maintaining the total state of the project. | -Attended the meetings and suggested improvements the project, | I learnt typescript and also learnt how to work as a part of a team.

## Christol
Your Lead Roles: Configuration leader, also responsible for UI & UX design
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/7-9/13 | 1.5 | 0.5 | 1 | 6. Commit to team repo and fixed a mistake | [6 empty] | 0.5 |  | 1. Fixed a git branching mistake of team repo
2 | 9/14-9/20 | 7.5 | 5.5 | 2 | 0. Researched git commit and branching stradegies, read documents of commitizen and husky 1. Researched and assessing project ideas 3. Wrote git criteria part of SPPP 4. Demonstrated the git criteria and team workflow I proposed to teammates 5. Determined git cirteria and team workflow, drew schematic diagrams | 1 | 0.5 |  | 1 | 1 | 2 |  |  | 1. Determined the git branching, commiting, issue mechanism and code review strategies 2. Wrote git cirteria section of SPPP | 1. Project is very similar to Amazon Pharmacy 2. An online pharmacy is too large for a semester long project, there will be a whole bunch of needed functions and security problems for a real one, we are not able to cover every part of it, it will definetly become a semi finished one, a draft, and nobody can really use it | 1. I had another project idea at the beginning, which we can cover and build a complete, can be used app based on it. Failed to persuade teammates, I'm at my wit's end. Expecting us to have a lot of trouble. | 1. Learn to configure comitizen and husky. 2. Start designing UI, determine the big picture and finish first few pages | 7h
3 | 9/21-9/27 | 7 | 5 | 2 | 0. Researched react+vite templates, read vite documentation 1. Researched similar competing products 5. Explored possibilities of turning our product into a medications fast delivery platform, and disscused with others about solutions to security risks and making project idea more reasonable | 2 | 1 |  |  |  | 2 |  |  | 1. Found a excellent react+vite+eslint+prettier template for our frontend | 1. Cought a fever this week, some works had to be delayed 2. Product requirements still not very clear | 1. Get our product requirements into shape | 1. Start my designing work | 12-14h
4 | 9/28-10/4 | 10.5 | 8.5 | 2 | 0. Researched about logo designing tools. 2. Designed the logo. Defined theme, topography and components styles. Built a landing page framework. | 1.5 | 7 | [6 empty] | 1. Designed the logo and defined UI style guidelines. | 1. Not sure about the entire flow of the product so upcoming design may be blocked. | 1. More EFFICIENT communication | 1. Do further configuration for the frontend template, and initialize the frontend project. 2. Finish the landing page design | 12-14h
5 | 10/5-10/11 | 15.5 | 12.5 | 3 | 0. Read documentation and learned about the usage of pre-commit hooks, lint-staged and cz-customizable 2. Finished the design of landing page 6. Added commitizen to the frontend project, customized the pre-commit messages, added eslint and prettier rules, initialized the folder structure, upgraded react and vite to latest versions | 1.5 |  | 6 |  |  |  | 5 |  | 1. Designed the landing page 2. Got the frontend project ready for upcoming development | 1. Team progress is a bit slow |  | 1. Move on to the design of shopping page and check out page. 2. Make a Figma presentation demo as a backup for the iteration 1 pre. | 12-14h
6 | 10/12-10/18 | 17 | 15 | 2 | 2. Finished the design of shopping page, shopping cart page, check out page, and prescription verification hints. Made a Figma demo for presentation. 7. prepare for presentation |  |  | 13 |  |  |  |  | 2 | 1. Designed the shopping page, check out page, payment page, and pop-ups. | 1. Taking me too much time ;( | 1. Developing is too slow. I'll try to boost it, if I will have less designing work next week. | 1. Contribute to the code, help implement the design 2. Start designing the doctor panel | 7h
7 | 10/19 - 10/25 | 5 | 3 | 2 | 0. read vite and MUI document 6. optimized configurations | 2 | [5 empty] | 1 |  | 1. optimized frontend configurations
8 | 10/26 - 11/1 | 9 | 7 | 2 | 0. read react router document 3. completed frontend router configuration; implemented half down of landing page | 1.5 |  | 5.5 | [5 empty] | 1. completed frontend router configuration 2. implemented half down of landing page |  |  | 1. Work as much as I can to prepare for presentation | > 16h
9 | 11/2 - 11/8 | 27.5 | 25 | 2.5 | 3. Implemented the whole landing page; implemented most of the shopping page; implemented pop up for prescription verification; worked together with Tsing to set up the http request pipeline between frontend and backend. |  |  |  | 25 |  |  |  |  | 1. Implemented the whole landing page 2. Implemented most of the shopping page 3. Implemented pop up for prescription verification 4. Worked together with Tsing to set up the http request pipeline between frontend and backend | 1. Too busy with developing new features to deal with UI flaws and bugs | Slow down and fix exsisting bugs | Fix UI bugs, link frontend to backend | 7h
10 | 11/9 - 11/15 | 8 | 6 | 2 | 6. Configured ESLint, prettier, TypeScript compiler, path aliases and git hooks after frontend and backend are merged into a monorepo project, enabled code check respectively for each side. | [6 empty] | 6 |  | 1. Configurations after FE and BE merged into one repository |  |  | Work on searching functions | 10h
11 | 11/16 - 11/22 | 12 | 10 | 2 | 3. Improved item card styles. Implemented searching by keyword for medicines on shopping page. Fixed UI bugs. |  |  |  | 10 |  |  |  |  | 1. Imporved item card. 2. Implemented searching by keyword function. 3. Fixed UI bugs on home page. |  |  | Implement category filter and item detail pop-up | 12h
12 | 11/23 - 11/29 | 16 | 14 | 2 | 3. Implemented searching by category function, intergrated it with home page category entries. Implemented item detail pop up. |  |  |  | 14 |  |  |  |  | 1. Implemented searching by category function. 2. Implemented item detail pop up. |  |  | Implement prescription generation page and retreive prescription function, and all other fixes to finish the project | ~20h
13 | 11/30 - 12/6 | 32 | 29 | 3 | 3. Implemented create prescription page, integrated with backend, including a dynamically searching for prescribed medication and adding to prescription function. Implemented retreiving prescription function. A lot of bug fixes and UI optimizations. |  |  |  | 29 |  |  |  |  | 1. Implemented create prescription page, and retreiving prescription function. 2. Bug fixes and optimization refactorings, help finish this project.

## Tsing
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 9/7-9/13 | 8 | 6 | 2 | 0 - learn java, express 1 - define high level requirements, 3 - talk about git flow, development flow, tools 6 - set up git 7 - research similar products, prepare presentation | 2 | 1 |  | 2 |  |  | 0.5 | 0.5 | 1. come up with git flow, development flow, some tools 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4、rearch vercel,figma,security tools | 1. not familar with communicate(no experience before) 2、not familar with new tools | 1. try to talk my opinions or views 2、spend more time to study | 1、determine some criteria about development 2、go for studying new tools or languages | 6
2 | 9/14-9/21 | 6.5 | 4.5 | 2 | 0. talk about with christol about commit criteria 1. Researched amzon pharmacy 2. Determined git cirteria and team workflow, drew schematic diagrams 4. Demonstrated the git criteria and team workflow I proposed to teammates | 1 | 0.5 | 2 |  | 1 |  |  |  | 1. Cooperated and Determined the git branching, commiting, issue mechanism and code review strategies 2. Discussed the complete workflow | 1. our pharmacy havn't functional barrier 2. We haven't completely built our pharmacy website | 1、turn to competitive products and get some brilliant features 2、quickly build our own thinking about E-commer pharmacy | 1. technology research 2、Active discussion | 5
3 | 9/21 - 9/27 | 6 | 4 | 2 | 0. study nodejs and express 1.search security defense | 2 | 2 | [6 empty] | 1. Cooperated and Determined tscript | 1. divide member into two end 2. prepare the unknow knowlege 3、talk about with zahit the nodejs framwork | 1、next week | 1. nodejs study 2、Figma study | 5
4 | 10/03 - 10/09 | 7.5 | 4.5 | 3 | 0. study nodejs and express 1.write down the security SPPP 5、talk about back-end framework | 2 | 1.5 |  |  |  | 1 |  |  | 1、come up with security document 2、determine back-end details | 1. Do we need sign up when patient shoping? 2、do we need add storage of medicine? | 1、talk with chritol, we decide to let users consider them sign up or not | 1. nodejs study 2、build up framework | 6
5 | 10/09 - 10/16 | 7 | 5 | 2 | 0. study mongodb 1.write down the security SDD 3 talk about interation of project 5、talk about back-end framework | 2 | 1 |  | 1 |  | 1 |  |  | 1、design the secutity doucument 2、sharing the flow of implement 3 find back-end templete | 1. Back-end templete 2 How to finsh the task of development? | 1、processing 2、sharing some experience to team | 2、build up back-end framework | 6
6 | 10/17 - 10/23 | 8 | 6 | 2 | 0. study mongose 6. know about amzon clound and mongo clound 7.write down security docs | 1 | [5 empty] | 4 | 1 | 1、complete mongodb clound and collection 2. start to develop user part | 1 some member don't familar with programing language and git flow | 1、sharing each other about technology 2 study by themselves | 1 finish back-end templete 2. write some filters in app.js file | 7
7 | 10/24 - 10/30 | 6 | 4 | 2 | 3.add filters in app.js file and finish user modules 4 write down test case and testing 5 talk with zahit about testing and project structure |  |  | 2 | 1 | 1 |  |  |  | 1. optimized frontend configurations 2. complete back-edn configurations | 1、should we need add jwt for every users? 2. how to interative jwt form back-end to front-end | 1 study some jwt knowleges 2 jwt generated by back-end, and every request need carry token in header | 1. complete user login and register 2 optimated whole project | 11
8 | 10/31 - 11/6 | 12 | 10 | 2 | 3. develop user login, register(full-stack) 5. talk with Chritol about request 6.Complete Interface Connections |  |  | 7 |  | 0.5 | 4.5 |  |  | 1. completed request connection 2. comleted user login and register 3、 completed jwt interaction | 1. How to show a prefect persentation | 1. passion 2. good PPT 3. confidence | 1. complete persentation 2 communicate with Ignaico about presentation | 12
9 | 11/7 - 11/13 | 15 | 13 | 2 | 3. optimizate user login and register 4. test our whole project 7. complete presentation and practice so more times |  |  | 3 | 2 |  |  |  | 7 | 1 finish presentation 2 ran all features 3 push everyone processing | 1. For No login users, should we verify token | 1. every user need carry token, if you are no-loin user, you must carry token="PASS" | 1. start next features 2. fix bugs | 6h
10 | 11/14 - 11/20 | 6 | 4 | 2 | 3. fixed some bugs 5. communicate with Christol about deployment |  |  | 2 |  | 2 |  |  |  | 1. came up with deployment way(herotu or aws cloud) | 1. How to enhance the motivation of team development | 1. Assign tasks to each team member and each person is responsible for his or her own module | 1. complete change password 2. support for patient login | 9h
11 | 11/21 - 11/27 | 9 | 7 | 2 | 3. develop user change password and support for patient 5. help member fix bugs |  |  | 5 |  | 2 |  |  |  | 1. completed user change password 2. supported for patient change password | 1. how to simulate non-prescription data | 1. add data in person | 1. search AWS deployment | 7h
12 | 11/28 - 12/4 | 7 | 5 | 2 | 5. talk with group1 about deployment 6. make a survey about aws cloud and apply for new aws account |  |  |  |  | 1 | 4 |  |  | 1. aws need add git hocks and clci scription, it will costs much time | 1. Can herotu support our two end project | 1. make a survery and try it | 1. deploy our project | 7h
13 | 11/5 - 12/11 | 9 | 7 | 2 | 3. develop user redux and show username 6. search state mangement way to mange common data like token 6. delopyment |  |  | 3 |  | 4

## Ignacio Moral
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirements Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | Time for type 0 tasks | Time for type 1 tasks | Time for type 2 tasks | Time for type 3 tasks | Time for type 4 tasks | Time for type 5 tasks | Time for type 6 tasks | Time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/04/2022-09/10/2022
2 | 09/11/2022-09/17/2022 | 5 | 3 | 2 | 0.- Relearn JS, start React tutorial 2.- Generate the Requirements for the project. 5.- Join Meetings with team members | 2 |  | 1 |  |  | 2 |  |  | 1. Write the Requirements Section. Both Functional and Nonfunctional 2.- Start writing the configuration tasks | 1.- React has a very high learning curve. If we were to use it, we need to be very familiar with it beforehand 2.- Requirements are very likely to change. Since is a product made by us entirely, we are still not 100% sure what we want to do. As they say "The client never knows what he wants" | 1.- Even if I don't really learn React, at least I should be able to have a clear understanding of CI/CD with React. 2.- We are using agile methodologies, so that will allow us to alter the requirements a bit if we so choose. | 2.- Keep learning React, especially the CI/CD 1.- Start developing prototypes | 3
3 | 09/18/2022-09/24/2022 | 6 | 4 | 2 | 0.- Keep learning React 1.- Start generating the requirements, rewrite them if needed. 5.- Assist meetings with the team members | 1 | 3 |  |  |  | 2 |  |  | 1.- Writing Non-Functional Requirements to security 2.- Keep writing Functional Requirements
| 09/25/2022-10/02/2022 | 5 | 2 | 3 | 1.- Keep track of requirements 5.- Meetings |  | 2 |  |  |  | 3 |  |  | 1.- User Stories
| 10/03/2022-10/09/2022 | 10 | 3 | 7 | 0.- MERN Stack Learning 1.- Working on Pivotal Tracker 5.- Team Meetings 7.- Reorganizing User Stories | 2 | 3 |  |  |  | 3 |  | 2 | 1.- Confirming configurations
| 10/10/2022-10/16/2022 | 9 | 6 | 3 | 1.- Reorganizing Pivotal Tracker to work as Epics 2.- Designing Class Diagrams and Business Logic Diagrams 5.- Meetings |  | 2 | 4 |  |  | 3 |  |  | 1.- Class Diagrams and Business Logic Diagrams 2.- Reclassification of User Stories | 1.- Discussion over Business Logic Diagrams | 1.- Communication is Key | 2.- Possible Class Diagram Reorganization to visualize Backend 2.- Updating program to better visualize Figma 4.- Testing backend 5.- Meetings 6.- Configurate DB | 11
| 10/17/2022-10/23/2022 | 6
| 10/24/2022-10/30/2022 | 7 |  | 3 | 0.- Mongoose Learning 2.- Mockup Prescription 5.- Team Meetings | 2 |  | 2 |  |  | 3 |  |  | 2.- Prescription Frontend Mockup
| 10/31/2022-11/06/2022 | 16 |  | 3 | 0.- Classes about Testing 3.- Prescription Model, Routes, and Controller created 4.- Testing creating new prescriptions 5.- Team Meetings | 3 |  |  | 6 | 4 | 3 |  |  | 3.- Prescription Backend
| 11/07/2022-11/13/2022 | 2 |  | 2 | 5.- Weelky Meetingss | [5 empty] | 2 |  |  |  | 4.- Need to update Prescription Model testing | 4.- Prescription Model testing sometimes fails. | 4.- Refactoring tests 4.- TDD 4.- Debugging | 2
| 11/14/2022-11/20/2022 | 3 | 2 | 1 | 4.- Testing new prescriptions 5.- Weekly meetings | 3 |  |  |  | 2 | 1 |  |  | 4.- Updated testing for Prescription Model | 3.- When a prescription gets created, a user should receive an email with the Prescription Number |  |  | 4
| 11/21/2022-11/27/2022 | 7 | 6 | 1 | 3.- Prescription Creation Update and Email Sending 5.- Weekly meetings | 7 |  |  | 6 |  | 1 |  |  | 3.- Prescription Creation Logic updated to be up to date with Front-End. Emails now also get sent whenever a new prescription is created.
| 11/28/2022-12/06/2022 |  |  |  | 1.- Completing Pivotal Tracker 5.- Meetings 7.- Documentation and Presentation |  | 2 |  |  |  | 2 |  | 5 | 1.- Updated status of multiple User Stories 7.- Updated Documentation for Current Iteration, and created outline of the Presentation

## Nivan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/7 - 9/13 | 4.5 | 3 | 0 |  | 2 | 1 |  |  |  |  | 0.5 | 1 |  |  |  |  | 7
2 | 9/14 - 9/20 | 3.5 | 3.5 |  |  | 1 | 1 |  |  |  | 0.5 |  | 1
3 | 9/21 - 9/27 | 4.5 | 4.5 |  | 0.Read react tutorials pertaining to router,form validation and props passing 3.started working on the frontend-ui using react nd implemented cart functionality | 2 | 2.5
4 | 9/28 - 10/4 | 3 | 3 |  | 3.Implemented form validation in cart |  |  |  | 3
5 | 10/5 - 10/11 | 2.5 | 2.5 |  | 3.Created a doctor Ui form for entering , deleteing and updating prescription |  |  |  | 2.5
6 | 10/12 - 10/18 | 2.5 | 2.5 |  | 3. Started working on the temporary firebase environment to manipulate and test data |  |  |  | 2.5
7 | 10/19 - 10/25 | 3 | 2 |  | 3.Implemented the Doctor Ui in working condition so that the Doctor can work on updating records |  |  |  | 3
8 | 10/26 - 11/1 | 4 | 4 |  | 0. Updskilled on Figma and Material Ui to help with the Item page | 4
9 | 11/2 - 11/8 | 3 | 3 |  | 3.Implemented the Item List Page using Figma and minor css with Critol's help |  |  |  | 3
10 | 11/9 - 11/15 | 3 | 3 |  | 0. Learnt the react testing library fundamentals | 3
11 | 11/16 - 11/22 | 4 | 4 |  | 4. Implemented the test cases for frontend testing 0.Learnt est basics and fundamentals | 2 |  |  |  | 2
12 | 11/23 - 11/29 | 1 | 1 |  | 7.Unclassified and setting up the enviornment for resolving issues | [7 empty] | 1
13 | 11/30 - 12/6 | 4 | 4 |  | 4.Implemented Front end test cases for the frontend ui |  |  |  |  | 4
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM

## Ryan Burns
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: Primary Team Leader, Back up: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
example | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/7 - 9/13 | 3 | 2 | 1 | 0-Spent time refamiliarizing myself with GitHub, git commands, and created our repository | 2 | [7 empty] | 1. Ran kickoff meeting and took minutes 2. Set up git, commit a test message on git | 1. Ran into a problem merging lab1 into main branch. Christol found a solution | 1. test GitHub on my own to become more comfortable with roadblcoks | 0 - Have first in person meeting 1 - choose a role - either requirement leader, QA leader... 2 - have SPPP document complete by Sunday 3 - refamiliarize myself with JavaScript & VSCODE | 7
2 | 9/14 - 9/20 | 5 | 3 | 2 | 0 - Reviewed documentation and Reviewed Team Leader Role 1 - SPP Research 2 - learning | 1 | 0.5 | 1.5 | [5 empty] | 0 - Created agenda for Sunday's meeting to "divide and conquor the SPPP document 1 - Researched already existing sites that already provide similar services to our project 2 - learning React | 0 - Creating an agenda that covered all aspects of SPPP doc was challenging 1- I could only go so far into an application without signing up for the service to fully understand what it offers 2- A bit of a learning curve for react | 2- keep on practicing with react | 0- Make sure all leaders are on the same page on their tasks 1- Start build of welcome page with necessary features. 2- Have team starting to think about what design pattern to use for our project 3- Learn more about QA leader role so I can be back up. 4- Learn more about React and Heroku | 4
3 | 9/21 - 9/27 | 6.25 | 4.25 | 2 | 0- learned more about react, practiced node.js with express 1-Discussed modifying requirements to suit a more specific user 2- 5 - drafted meeting agendas 7 - researched similar programs and my backup role QA Leader and what the responsibilites are | 2.5 | 0.5 |  |  |  | 0.25 |  | 1 | -Created ppt showing team how an online pharmacy works. -Narrowed down our user to a person who needs to take medication daily | -Not familiar with React -Not familiar with Eslint or other JS extensions -Implementation and design Leaders need to collab and code needs to be pushed to GitHub | - React & Eslint plan: research free lessons online |  | 6
4 | 9/28 - 10/4 | 3.5 | 1.5 | 2 | 0 - learning 1 - updated high level requirements |  | 0.5 | 1 | [5 empty] | 1. Updated SPPP doc considering the professors feedback from iteration 0 | 1 - I need my team's approval 2 - I've never created a UML diagram for JS before... | 1- I plan to discuss it at tomorrows meeting. Check with team that everone is on board with using pivotal tracker to be our AGILE tool. 2- I'm trying to use my Java UML experience and apply it to this group project | 0 - continue my research on reach and look up how to add a login 0 - Figure out how to use pivotal traker | 12
5 | 10/5 - 10/11 | 6.25 | 3.25 | 3 | 0 - learned more about React and git commands 2 - gave feedback and ideas on Figma UI template 5 - Coached team on real world examples of an online pharmacy to help hone in on our requirement | 2 |  | 0.5 |  |  | 0.75 |  |  |  | - React is a challenge to learn, but I'm learning little by little | - Spend at least 2 hrs next week on coding in React and committing my changes to Github |  | 6
6 | 10/12 - 10/18 | 8 | 6 | 2 | 0 - familiarized myself with the Git Commit Standards we set & did more research on React and TS 1 - In Friday's meeting I steped through all requirements in our SPPP document with team 3 - Did some refactoring on code in the dev branch of our project 5 - make projeect plan & created agendas for meetings 6 - started to code search bar in dev code in GitHub 7 - Finalized SDD and prepped for presentation | 2 |  |  | 0.5 | 1 | 0.5 | 1 | 1 | 3 - I started contributing changes to the code in GitHub to encourage participation 5 - Adding Daily Standup (round-robin) to our meetings to structure our commitments | 1 - unsure how to satisfy Doctor's requiremnets at this time 3 - Had to add a step to the git commit criteria on my machine - but was able to get my commits to work | - Learning curve with React & TS - Asked for help from Nivan to help me code in React, jsx and tsx. | 1 - Pull another Users Story and work on it until completion 3 - Refactor existing code to fit the design leaders (figma) creation 5 - Encourage all team members to have their hands in the code | 7
7 | 10/19 - 10/25 | 2 | 0 | 2 | spent time working on react components 1.5 hrs Contributed code the the dev/fe branch learned about Material UI
8 | 10/26 - 11/1 | 7 | 5 | 2 | 0 - Learned how to do tests in Vitest 2 - worked on implementing Figma design into front end 3 - Volunteered to work on top half of landing page 5 - Set goals for the team to meet iteration deadline | 1 |  | 1.5 | 2 |  | 0.5 |  |  |  | 0 - thinking of what tests to run is difficult after code is created 2 - Material UI is challenging to work with in React b/c there is overlap in layout 3 - Design is challenging to implement in the front end with material UI issue | 3 - Pushed front end code for landing page to GitHub branch ryan/welcome and requested a pull request and added bugs to issues in GitHub. And now working on the Categories component | - write unit tests for the code base - ensure functionality works - prepare for iteration 2 presentation | 8
9 | 11/2 - 11/8 | 8 | 5.5 | 2.5 | 0 - Tried using Source Control in VS Code 3 - coded the categories section and began carousel in the front end 7 - Organized meetings for team discussion and tried creating an environment where people can share their thoughts | 1 |  |  | 4 |  |  |  | 0.5 | 0 - used a mix of VS Code Branch control, but I'm more comfortable using git on the command line 3 - pushed the categories section along with the carousel frame to github and created a pull request for the front end team to review | 3 - Found mui carousel in NPM, but I don't know how to implement the example code from JS to TypeScript | 3- Plan to ask Zahit for help on creating carousel using the example I found
10 | 11/9 - 11/15 | 3 | 1 | 2 | 0 - Looking up ways to implement the shopping cart feature using react and typescript | 1 | [9 empty] | 0- online resources are a challenge to parse through especially examples with material ui
11 | 11/16 - 11/22 | 10 | 8 | 2 | 0 - Researched Shopping Cart Logic 3 - Tried getting Shopping cart logic to work in code | 5 |  |  | 3 |  |  |  |  | 0 - found online resources that demonstrated cart logic implementation 3 - tried making cart logic work with shopping page | 3 - I ran into bugs and errors trying to implement the code | 3- Let the team know immediately of my road blocks |  | 6
12 | 11/23 - 11/29 | 5 | 3 | 2 | 3 - Added 100+ documents to MongoDB |  |  |  | 3 |  |  |  |  | 3 - Because no API could be found for ovver the counter products at a pharmacy I created json files to import over 100 items to our database | 3 - Different categories did not have generic names, so in the name space I defined what the product was and the brand name was entered in as the brand name | Offer support to team wherever it's needed | Support Team in anyway I can to make the implementation of joining the front end to the backend as simple as possible | 7
13 | 11/30 - 12/6 | 5 | 3 | 2 | 5 - Created the agenda with detailed requirements and discussion points prior to our presentation 6 - Added my feature branch to github 7 - Documentation updates | [5 empty] | 2 | 1 |  | 6 - Though I couldn't figure out how to get the shopping cart feature to work I did develop the figma design for the cart button and other tsx files that might be helpful for more experienced developers to reference 7 - volunteered to manage the updates to the SDD and SPPP documents for this iteration | 6 - The cart code was challenging and I was not able to create a solution on my own | I offered my team the code I created as a tool to work from but it was optional |  | 6
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM

## Zahit
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: QA Leader, Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/7 - 9/13 | 5 | 3 | 2 | 0 - reading some git and github documents 1 - looking for some project ideas | 1 | 2 | [6 empty] | 1- Set up git and commit to project repo 2- Timekeeper at meeting 2 |  |  | 0 - Decide a project 1 - Choose a project role 2 - Research the topics related with project role | 10
2 | 9/14 - 9/20 | 10.5 | 9.5 | 1 | 0 - Research about project functions and requirements 1 - Research about branching strategies 2 - Research about QA Plan and tools 3 - Write QA Plan in SPPP 4 - Prepare a part of presentation in SPPP | 2 | 1 | 4 | 1 | 1.5 |  |  |  | 1 - Acquired QA Leader role and backup Project Leader Role 2 - Timekeeper and minutestaker at meeting 3 3 - Write Timeline in Management Plan and QA Plan sections in SPPP | 1 - Essential Features may be extended during Iteration 1 |  | 1- Set up Prettier and ESLint 2- Contribute setting up feature branches 3- Integrate Prettier + ESLint and Unit Tests in pre-commit hook 4- Main Page Design | 15
3 | 9/21 - 9/27 | 12 | 10 | 2 | 0 - Research about ESLint and Prettier 1 - Prepare GitHub branches 2 - Research about React.JS templates 3 - Prepare and participate in presentation for Iteration 0 4 - Design a more secure and more logical use case for the project considering Prof.'s feedback from Iteration 0 | 3 | 1 | 2 | 4 |  |  |  |  | 1- Created some feature and chore branches in GitHub 2- Determined and prepared the npm packages to be used in project 3- Participated in presentation for Iteration 0 | 1- We have re-defined some essential features but we need to discuss further next week |  | 1 - Prepare the testing library 2 - Research Husky hooks 3 - Update SPPP document according to new use cases | 10
4 | 9/28 - 10/4 | 8 | 6 | 2 | 0 - Prepare testing library 1 - Integrate js libraries with Christol's React template 2 - Update SPPP document | 2 | 2 | 2 | [5 empty] | 1 - Decided to use Vitest for testing and added library to package.json 2 - Tweaked the template, configured Husky scripts and pushed frontend template to GitHub 3 - Updated project overview and features in SPPP document |  |  | 1- Learn PivotalTracker and contribute to user stories 2 - Study some React js tutorials 3 - Study Nivan's React code | 8
5 | 10/5 - 10/11 | 8 | 6 | 2 | 0 - Create user stories in PivotalTracker 1 - Study React Js tutorials and Nivan's code | 2 | 4 | [6 empty] | 1 - Created user stories | 1- I feel we are a little behind of schedule. We need to start developing soon |  | 1 - Research backend templates 2 - Prepare some part of SDD document 3 - Study Express Js and MongoDB | 8
6 | 10/12 - 10/18 | 11 | 10 | 1 | 0 - Research backend templates 1 - Study Express JS 2 - Study Vitest 3 - Prepare Project Structure and Database design in SDD 4 - Minutes taker in meeting 10 5 - Update Security Design section in SDD | 2 | 3 | 1.5 | 2 | 0.5 | 1 |  |  | 1- Added project structure and database desing into SDD 2 - Updated Security Design in SDD regarding Prof. lecture on October 19 3 - Minutes taker in meeting 10 |  |  | 1 - Distribute user stories 2 - Start backend development 3 - Try to apply Figma design to our codebase | 12
7 | 10/19 - 10/25 | 18 | 16 | 2 | 0 - Configure a cloud mongoDB database for backend 1 - Create sample "Items" API 2- Complete Items API with route and controllers 3 - Code Item API tests 4 - Code Navbar for main page | 3.5 | 4.5 | 3.5 | 2 | 2.5 |  |  |  | 1 - Added Item Model, controllers, routers for backend 2 - Added Navbar and sub components for frontend | 1- We need more contribution to the source code | 1 - Address development pace in the meeting 2 - Talk about work sharing and how's everyone doing | 1 - Complete tests for ItemApi and Navbar 2 - Add search functionality and display results 3 - Try to add item list page to the frontend 4 - Work on issues from code-review | 20
8 | 10/26 - 11/1 | 14 | 12 | 2 | 0 - Continue coding Navbar for main page 1 - Fix bug "component beneath fixed Appbar" 2 - Add Drawer component 3 - Fix coding style referring the feedback from Code Review 4 - Added Item query validation 5 - Reviewed Ryan's Welcome component and refactored it | 2.5 | 1.5 | 3.5 | 1.5 | 1 | 2 |  |  | 1 - Fixed NavBar bug 2 - Added Drawer component 3 - Code review and update 4 - Item Query validation |  |  | 1 - Check task implementation progress 2 - Check if everyone implements tests 3 - Utilize mongo-in-memroy-db library 4 - Initialize basic components and page settlement for shopping page | 14
9 | 11/2 - 11/8 | 17 | 15 | 2 | 0 - Reviewed Tsing's User Model, API, and error handler. Ignacio's prescription model, API. Refactored their code. 1 - Detected code smells in Item query validation. Refactored it. 2 - Added tests and mongo-in-memory-db for testing 3 - Added structure and basic components for item list page 4 - Meeting Minutes document 5 - Created STD document 6 - Presentation Review with Tsing&Ignacio | 3 | 3 | 3 | 3 | 0.5 | 1.5 | 1 |  | 1 - Code review and update 2 - Query validation refactoring 3 - Basic page settlement for shopping page 4 - Document meeting #16 5 - STD document | 1- We need more contribution to the source code | 1 - Talk about distribution of remaining tasks 2 - Remind PivotalTracker update to Requirement Leader | 1 - Frontend-Backend interactions 2 - Start security related implementations | 14
10 | 11/9 - 11/15 | 10 | 9 | 1 | 0 - Merging backend-frontend branches into 1 branch 1 - Research about react-frontend testing and adding simple test cases 2 - Planned the distribution of remaining work in the meeting | 4.5 | 4 | 0.5 | [5 empty] | 1- Merging branches 2- Adding front-end tests
11 | 11/16 - 11/22 | 8 | 6 | 2 | 0 - Meeting with Ryan about his implementation issue 1 - Refactoring and bug fixing ItemAPI for frontend needs 2 - Checkout page ui implementation | 0.5 | 2 | 3.5
12 | 11/23 - 11/29 | 18.5 | 16.5 | 2 | 0 - Checkout page ui implementation 1 - Meeting with Ryan, talking about inserting medicine into our DB 2 - Updating MongoDB and API's and adding documentation in Postman shared workspace for frontend developers 3 - Reviewing Ryan's and Ignacio's commits 4 - Meeting with Christol about latest implementations | 10 | 0.5 | 4 | 1 | 1 |  |  |  | 1- Partly completed checkout page and merged 2- Updated APIs and merged 3- Performed code reviews and merged | 1- It looks like some members will need to work harder to cover other member's unfinished work |  | 1 - Implementation of cart icon and functionality 2 - Add more ui component test, and add end-to-end test with cypress 3 - Perform security related test | 20
13 | 11/30 - 12/6 | 24 | 21 | 3 | 0 - Research about global state management for shopping cart functionality 1 - Implementing shopping cart state management 2 - Checkout page integration with state management and backend 3 - Review of whole project and bug fixing 4 - Project video and contribution to presentation slides | 3 | 6 | 5 | 5 | 2 |  |  |  | 1- Finished Checkout page and merged 2- Finished integrating react-redux state management 3- Performed final project review and bug fixing 4- Prepared my part, testing section and project video for final presentation
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM